## Slide 1
NWSL TSX Launch Week
PANINI POST PLAN
NWSL TSX Launch Week
PANINI x NWSL 2026 Launch • March 11, 2026
WORKFLOW
Approval to Publish
Structured for client review, creative signoff, and launch execution.
USE
Post Plans
Reusable export mapped for Panini rollout decks.

## Slide 2
NWSL TSX Launch Week
MOCKUP REVIEW
Mockup Review
Overview
SUMMARY
Review the exact NWSL launch cadence, social copy, mockups, and approval lanes before anything is exported or posted. Execute as one coordinated rollout: TSX hero reveal, league and NWSLPA amplification, then weekend club pickup with matchday framing. Every row below should remain presentation-ready without operator cleanup. Use this review to clear the launch sequence now…
DECK
NWSL TSX Launch Week
NWSL TSX Launch Week
FOCUS
Client-facing story, operational readiness, and creative coverage stay aligned in one deck.

## Slide 3
NWSL TSX Launch Week
PLAN METRICS
Mockup Snapshot
Snapshot
POSTS
7
7 launch placements are currently mapped.
READY TO EXPORT
1/7
1 packet are green across approval, copy, and creative.
OPEN PACKET ISSUES
1
1 packet are actively blocked or in revision.
READOUT
Panini Brand Lead and TSX Partnership Lead have cleared the plan, while NWSL Social and NWSLPA Comms still need to…

## Slide 4
NWSL TSX Launch Week
HERO CREATIVE
TSX Hero Reel
Hero
NARRATIVE
Hero launch • Mar 11, 8:00 AM • Instagram Reel • Posted by Panini Social • Approval Panini Ops • Required Copy • Keep the first…

## Slide 5
NWSL TSX Launch Week
LAUNCH CREATIVE 1
Hero + Support 1
Assets
Post 01 • Launch Carousel
Launch support • Mar 11, 8:30 AM • Instagram Feed • Posted by Panini Social • Approval NWSL Social • Required Copy •…
Post 02 • Athlete Gifting…
Launch support • Mar 11, 10:00 AM • TikTok • Posted by Panini Creator Team • Approval NWSLPA Comms • Suggested Copy •…

## Slide 6
NWSL TSX Launch Week
LAUNCH CREATIVE 2
Hero + Support 2
Assets
Post 01 • League Toolkit X…
Distribution handoff • Mar 11, 11:15 AM • X / Twitter • Posted by NWSL Social • Approval NWSL Social • Required Copy •…
Post 02 • Partner LinkedIn…
Distribution handoff • Mar 11, 1:00 PM • LinkedIn • Posted by Partnerships Team • Approval Panini Partnerships •…

## Slide 7
NWSL TSX Launch Week
LAUNCH CREATIVE 3
Hero + Support 3
Assets
Post 01 • NWSLPA Amplification
Distribution handoff • Mar 11, 3:00 PM • Instagram Feed • Posted by NWSLPA Social • Approval NWSLPA Comms • Required…
Post 02 • Weekend Matchday…
Carry-forward • Mar 13, 9:00 AM • Instagram Feed • Posted by Club Social Leads • Approval League Social • Suggested Copy…

## Slide 8
NWSL TSX Launch Week
OPEN APPROVALS
Approval Status
Readiness
DECISION
Decision Status
Panini Brand Lead and TSX Partnership Lead have cleared the plan, while NWSL Social and NWSLPA Comms still…
DIRECTION
Stakeholder Path
Panini Brand Lead, NWSL Social, and 2 more are in the active review loop, and Panini Social, Panini Creator…
WATCHOUTS
Open blockers
1 placement is still missing tag instructions; 1 slot has no linked asset yet; 6 slots still need post-level…

## Slide 9
NWSL TSX Launch Week
LAUNCH SEQUENCE 1
Hand-off Order 1
Schedule
SLOT 1
Post 01 • TSX Hero Reel
Hero launch • Instagram Reel • Posted by Panini Social • Approval: Panini Ops • Approved • Required Copy • Copy Locked • Creative Final •…
SLOT 2
Post 02 • Launch Carousel
Launch support • Instagram Feed • Posted by Panini Social • Approval: NWSL Social • Approval Pending • Required Copy • Copy In Review •…
SLOT 3
Post 03 • Athlete Gifting…
Launch support • TikTok • Posted by Panini Creator Team • Approval: NWSLPA Comms • Approval Pending • Suggested Copy • Copy In Review •…
SLOT 4
Post 04 • League Toolkit X…
Distribution handoff • X / Twitter • Posted by NWSL Social • Approval: NWSL Social • Changes Requested • Required Copy • Copy Draft •…
SLOT 5
Post 05 • Partner LinkedIn…
Distribution handoff • LinkedIn • Posted by Partnerships Team • Approval: Panini Partnerships • Approval Pending • Suggested Copy • Copy…
EXECUTION
Sequence titles capture the publish order; descriptions hold timing, ownership, and CTA direction.

## Slide 10
NWSL TSX Launch Week
LAUNCH SEQUENCE 2
Hand-off Order 2
Schedule
SLOT 1
Post 01 • NWSLPA Amplification
Distribution handoff • Instagram Feed • Posted by NWSLPA Social • Approval: NWSLPA Comms • Approval Pending • Required Copy • Copy In Review…
SLOT 2
Post 02 • Weekend Matchday…
Carry-forward • Instagram Feed • Posted by Club Social Leads • Approval: League Social • Approval Not Requested • Suggested Copy • Copy…
SLOT 3
Open Slot 3
Reserve for additional supporting content, revisions, or amplification if needed.
SLOT 4
Open Slot 4
Reserve for additional supporting content, revisions, or amplification if needed.
SLOT 5
Open Slot 5
Reserve for additional supporting content, revisions, or amplification if needed.
EXECUTION
Sequence titles capture the publish order; descriptions hold timing, ownership, and CTA direction.

## Slide 11
NWSL TSX Launch Week
STAKEHOLDER PACKETS 1
Copy, Owners & Tags 1
Details
POST 1
Post 01 • TSX Hero Reel
READY • Objective: Open the partnership with a national launch frame that every league, player, and club handle can follow without rewriting the story. • ASK: Can we lock this hero…
POST 2
Post 02 • Launch Carousel
NOT READY • Blockers: Approval Approval Pending • Copy Copy In Review • Creative Creative In Review • Objective: Turn the hero announcement into a fast-moving opening-week sequence…
POST 3
Post 03 • Athlete Gifting…
NOT READY • Blockers: Approval Approval Pending • Copy Copy In Review • Objective: Add player proof so the partnership feels earned in-feed and not just announced from the brand…
POST 4
Post 04 • League Toolkit X…
NOT READY • Blockers: Approval Changes Requested • Copy Copy Draft • Creative Creative Missing • Objective: Turn the hero story into a usable club toolkit so local handles can post…

## Slide 12
NWSL TSX Launch Week
STAKEHOLDER PACKETS 2
Copy, Owners & Tags 2
Details
POST 1
Post 01 • Partner LinkedIn…
NOT READY • Blockers: Approval Approval Pending • Copy Copy Draft • Creative Creative In Progress • Tags missing • Objective: Translate launch energy into a partner-safe business…
POST 2
Post 02 • NWSLPA Amplification
NOT READY • Blockers: Approval Approval Pending • Copy Copy In Review • Creative Creative In Review • Objective: Push the launch through the player association handle so the…
POST 3
Post 03 • Weekend Matchday…
NOT READY • Blockers: Approval Approval Not Requested • Copy Copy Draft • Creative Creative In Progress • Objective: Carry the launch into matchweek behavior so the partnership…
POST 4
Optional Slot 4
Use this space for an alternate creative, partner variation, or backup publish window.

## Slide 13
NWSL TSX Launch Week
COMMENTS & DISCUSSION
2 comments attached
Readiness
DECISION
NWSL Social (NWSL)
League team is aligned on the rollout shape. Final tag list can lock once the TSX hero reel export is approved.
DIRECTION
NWSL Social (NWSL)
League Toolkit X Post (Post 4): requesting two changes before approval. (1) The player tag list needs to be final and attached to…
WATCHOUTS
Launch Watchouts
No launch watchouts captured.

## Slide 14
NWSL TSX Launch Week
Partner Signoff
NWSL TSX Launch Week
Generated as a reusable rollout deck for review, creative signoff, and publish execution.